## Gantt Chart
GANTT CHART TEMPLATE
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9
[6 empty] | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su
BASIC FEATURES
| Interface | 2018-01-05 | 2018-01-08 | 2 | Tyler | bar: WEEK 1 M to WEEK 4 Su; WEEK 6 M to WEEK 6 Su
| Menu |  |  | 0 | Dilshawn | bar: WEEK 1 M to WEEK 4 Su; WEEK 6 M to WEEK 6 Su
| Ships | 2018-01-11 | 2018-01-16 | 4 | Kashyap | bar: WEEK 1 M to WEEK 4 Su; WEEK 6 M to WEEK 6 Su
| Ship placement | 2018-01-14 | 2018-01-19 | 5 | Dilshawn | bar: WEEK 1 M to WEEK 4 Su; WEEK 6 M to WEEK 6 Su
| User Input | 2018-01-17 | 2018-01-21 | 3 | Sultan | bar: WEEK 1 M to WEEK 4 Su; WEEK 6 M to WEEK 6 Su
| keyboard input |  |  |  | Sultan | bar: WEEK 1 M to WEEK 4 Su; WEEK 6 M to WEEK 6 Su
| Computer Input | 2018-01-20 | 2018-01-23 | 2 | Sultan | bar: WEEK 1 M to WEEK 4 Su; WEEK 6 M to WEEK 6 Su
MEDIUM
| GUI | 2018-02-05 | 2018-02-08 | 4 | Tyler | bar: WEEK 4 M to WEEK 6 Su
| Computer logic | 2018-02-08 | 2018-02-13 | 4 | Sultan | bar: WEEK 4 M to WEEK 6 Su
| Random generator | 2018-02-11 | 2018-02-16 | 5 | Kashyap | bar: WEEK 4 M to WEEK 6 Su
| In game menu | 2018-02-14 | 2018-02-23 | 8 | Dilshawn | bar: WEEK 4 M to WEEK 6 Su
| mouse input |  |  |  | Kashyap | bar: WEEK 4 M to WEEK 6 Su
ADVANCED FEATURES
| Animation | 2018-03-05 | 2018-03-08 | 4 | Tyler
| data/code efficiency |  |  |  | Everyone
| New version of battleship | 2018-03-08 | 2018-03-13 | 4 | TBD
| Volume/background music/sound effects | 2018-03-11 | 2018-03-16 | 5 | Tyler/Kashyap
| 2 player mode | 2018-03-17 | 2018-03-21 | 3 | TBD
| Anti cheat for 2 player mode | 2018-03-20 | 2018-03-25 | 4 | TBD
| Complete debug |  |  |  | Everyone
| Computer AI | 2018-03-20 | 2018-03-25 | 4 | TBD
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])